WEEKLY DELIVERY PLAN · DISCOVERY & SELECTION What we deliver, week by week Deliverables per week, the assumptions they rest on, and what we need from other teams to hold the dates. PROGRAMME T&F Reader — 8-Week Graduate Prototype WE OWN Institution listing · Institution selection · Catalogue browse · Unified search TARGET Feature-complete on mock data by end of Week 3 · integration closes Week 4 WEEKS W1 10–14 Aug · W2 17–21 Aug · W3 24–28 Aug · W4 31 Aug–4 Sep 2026

01

What we are building

Six areas. Everything in them is working against mock data by the end of Week 3; integration with the real services runs through Week 4.

| Area | What it covers |
| --- | --- |
| Catalogue | Browse three OPDS feeds — Books, Journals, Audiobooks — as three tabs, each paginated. Full catalogue before sign-in, scoped to entitlements after. |
| Search & filter | Search on title, author and subject, with exact match on DOI and ISBN. Filters for content type, subject, publisher, year, access state and Open Access. Sort, result count, and voice input. |
| Institutions | Browse and search institutions, view detail, select one, remember it, change or clear it, and route to the right sign-in. |
| Access & actions | One rule deciding the single action on every item — Read, Download, Borrow, Subscribe, Sign in or Waitlist — and the loan that Borrow creates. |
| Item detail | Full metadata for books, journals, articles and audio, with the same action model as the list. |
| App & states | Shell, navigation, shared components, and the loading, empty, error and offline states across every surface. |

WHAT WE ARE NOT BUILDING The reader itself and the downloads library belong to the reader team. Authentication screens and the borrow service belong to the authentication team. The catalogue feeds and institution data belong to the catalogue team. We call all three; we do not build them. A purchase or Buy flow is out of scope for the prototype entirely.

02

What we are assuming

Every assumption below is currently unconfirmed. Each one is already built against a stub, so none of them blocks us — but if one turns out wrong, the work it touches is reshaped rather than merely extended. They are listed roughly in order of how much would change.

| # | Assumption | If it is wrong |
| --- | --- | --- |
| 1 | The catalogue team can serve a full catalogue to a user who is not signed in | The whole browse-first model changes. This is the single biggest one. |
| 2 | They will add a per-item field telling us the access tier — Open Access, Subscription or Elite. OPDS has no equivalent, so this is something they must add rather than expose | No access states, no badges, no correct action anywhere. Longest lead time of anything we are asking for. |
| 3 | After sign-in we receive a feed already scoped to entitlements, or a full feed with flags we can filter on | We filter locally. Slower, but workable. |
| 4 | The three feeds are split by content type and shown as three tabs, not merged into one list | Merging means cross-feed deduplication, merged pagination and re-ranking three result sets that cannot be compared. Significant added work. |
| 5 | Articles sit inside the Journals feed, and that feed is flat rather than nested by volume and issue | Detail and navigation change for journals and articles. |
| 6 | Search matching, ranking, sorting and filtering are ours to build. OPDS supplies only a search link | If the catalogue team can rank server-side, we do less. Assuming we build it is the safe direction. |
| 7 | Institution data has no OPDS equivalent, so we define its shape and they confirm it | We adopt their shape instead. Low cost. |
| 8 | A loan is needed for anything the user can take a copy of. Open Access and Subscription need Borrow first; Elite is read-only so never does | The action model changes on every screen. |
| 9 | The authentication team can tell us, in one call, which of a page of items a user has on loan | Forty results would mean forty calls. This is the likeliest cause of a visibly slow app. |
| 10 | A signed-out user reading Open Access needs no loan, because there is no borrower | A guest would have to sign in before reading anything. |
| 11 | Subscribe applies only to individual accounts, never institutional ones | An extra action appears on institutional feeds. |
| 12 | We hold the item a user tapped across the whole sign-in journey and return them to it | Users land back on the home screen after signing in. Ours to solve either way. |
| 13 | Sample data arrives in Week 1 and real endpoints in Week 3 | Weeks 1 and 2 are unaffected — they run on our own fixtures. Week 4 absorbs the delay. |

03

Week by week

HOW TO READ THIS Weeks 1 to 3 are ours alone and run entirely on mock data, so nothing in them depends on another team arriving on time. Week 4 is integration, and is the only week whose content depends on services outside the team. It is deliberately left light.

Week 1 — 10 to 14 August · Foundations

Delivers

Design tokens, shared component library, app shell and navigation — all merged before feature work starts

The internal content model, and adapters turning all three OPDS feeds into it

Identifier handling, so DOI and ISBN become searchable fields

Mock data covering every content type and every access state

Catalogue browse with feed tabs and pagination

Search with matching and ranking, working over mock data

Institution list, detail and search

Needs from others

Sample catalogue feed and sample institution list — hand-written is fine, shape matters more than content

Confirmation that an unsigned-in user can fetch the full catalogue

Agreement on the per-item access-tier field

The sign-in handoff contract, even if the screen lands later

DONE WHEN The catalogue is browsable and searchable on mock data, institutions can be searched and viewed, and every contract request has gone out in writing.

Week 2 — 17 to 21 August · Access, loans and detail

Delivers

Institution selection, remembered across restarts, changeable and clearable

Routing into institutional or personal sign-in, carrying institution context

The access rule producing exactly one action per item, and the tier badge on every card

Borrow creating a loan, and the button changing to Read and Download once it succeeds

Loan state fetched and cached, so the right action shows on a full page of results

The tapped item held across sign-in and restored afterwards

Item detail for books, journals, articles and audio

Filters, sort, result count, and search state that survives navigation

Voice input feeding the same search

Needs from others

A way to read the signed-in user’s session and entitlements

A single call returning loan state for a page of items

The Borrow endpoint, or its contract so we can build against it

A sign-in screen we can route into, even a mock one

DONE WHEN All three states — signed out, institutional and individual — can be walked end to end on mock data, with the correct single action on every item and the return-to-item journey working.

Week 3 — 24 to 28 August · Hardening, and the first real data

Delivers

Loading, empty, error and offline states across every surface

Waitlist and access-restricted states, and Borrow failure handling

Every screen checked against every state — the largest single block of the week

The access-state filter, once the field exists

Institution list working offline, since sign-in depends on it

Real feeds and real sessions wired in as they become available

Needs from others

Real catalogue and institution endpoints

Real session and entitlement access

DONE WHEN — THE ONE THAT MATTERS Everything we own is finished, hardened and demonstrable. From this point anything outstanding is another team’s service, not our feature work.

Week 4 — 31 August to 4 September · Integration

Delivers

Mock data swapped for real catalogue, session, loan and reader services

Fixes for any differences between the assumed and real data shapes

Accessibility pass and the behaviour-driven test suite

Buffer for anything that arrived late

IF NOTHING LANDS This week is deliberately underfilled. If everything arrives on time we finish ahead. If nothing does, we demonstrate on mock data and say so plainly, rather than discovering the gap on the day.

04

What we need, and by when

Grouped by who we need it from. Everything here already has a stub behind it, so a late answer costs us reshaping rather than idle time — except the four marked critical, which have no workable substitute.

From the catalogue team

| Need | By | Why it matters |
| --- | --- | --- |
| Confirmation that an unsigned-in user can fetch the full catalogue | Wk 1 | CRITICAL — the browse-before-sign-in model depends on it |
| A per-item access-tier field. OPDS defines nothing equivalent, so this is an addition | Wk 1 | CRITICAL — without it there is no badge and no correct action anywhere |
| Sample catalogue feed and sample institution list | Wk 1 | We build our own if it is late, then reshape |
| What the three feeds are split by, and what to call them | Wk 1 | Drives the tab bar; kept configurable so a change is cheap |
| Whether a title can appear in more than one feed | Wk 1 | Decides whether we need to remove duplicates |
| Whether search reaches you per feed or across all three | Wk 1 | Global search is significantly more work than per-feed |
| How DOI and ISBN are written in the feed | Wk 1 | Needed for exact-match search |
| Whether the feed is scoped after sign-in, or we filter it | Wk 1 | Changes where entitlement filtering happens |
| Pagination style, result counts, and how sorting is expressed | Wk 2 | We fall back to local handling |
| Which metadata fields are reliably populated | Wk 2 | We render what exists |
| Whether journals are flat or nested | Wk 2 | Changes journal navigation |
| Institution field list, sign-in type, and logos | Wk 2 | We use placeholders otherwise |

From the authentication team

| Need | By | Why it matters |
| --- | --- | --- |
| One call returning loan state for a page of items | Wk 1 | CRITICAL — per-item calls would make a page of results visibly slow |
| The sign-in handoff contract — what we pass, how control returns | Wk 1 | We route to a placeholder otherwise |
| Whether sign-in leaves the app, and how control comes back | Wk 1 | Decides whether we store the tapped item on disk |
| Whether the session tells us institutional from individual | Wk 1 | Decides when Subscribe appears |
| What an individual account is entitled to beyond Open Access | Wk 1 | Shapes the individual feed |
| How we read the signed-in user’s session and entitlements | Wk 2 | We mock the shape otherwise |
| The Borrow endpoint and its full set of failure responses | Wk 2 | We build to the written contract |
| Copies and availability, so we can show a waitlist before the user taps | Wk 2 | Otherwise we only show it after a failure |
| Loan duration, and what happens when one lapses mid-read | Wk 2 | We treat a lapsed loan as no loan |
| Session expiry behaviour while browsing | Wk 2 | Handled generically otherwise |
| A mock sign-in screen we can route into | Wk 2 | Placeholder otherwise |

From the reader team

| Need | By | Why it matters |
| --- | --- | --- |
| How we launch the reader from an item | Wk 2 | Stubbed otherwise |
| How a download is handed over, and who stores it | Wk 2 | Stubbed otherwise |
| Confirmation that Elite content cannot be downloaded at your end either | Wk 2 | We simply never offer it |
| Who shows the downloaded indicator on catalogue items | Wk 2 | Omitted initially |
| Whether signed-out users can download, and who stores it | Wk 2 | Omitted otherwise |

From leadership

| Need | By | Why it matters |
| --- | --- | --- |
| Confirmation that catalogue browse and unified search are ours to build | Wk 1 | CRITICAL — most of this plan assumes it |
| Sign-off that the catalogue narrows to entitled content after sign-in | Wk 1 | Reverses a statement in the signed design document |
| Sign-off that the three feeds appear as three tabs rather than one list | Wk 1 | Also differs from the design mockups |
| Confirmation that a purchase flow is out of scope | Wk 1 | No team currently owns one |